## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Dashboard
| Table 1 | Dashboard
Monday-Friday Plan
| Table 1 | Monday-Friday Plan
MVP Task Tracker
| Table 1 | MVP Task Tracker
Post-MVP
| Table 1 | Post-MVP
Options
| Table 1 | Options

## Dashboard
InScape Giveaway MVP Progress Dashboard
MVP Phase Setup
Week Start | 2026-05-04
Weekly Structure | $280/week
Working Days | 5 days/week
Main Focus | Core Giveaway MVP
Timeline View | Monday to Friday
Current Target | Launchable / testable MVP
Tracker Purpose | Keep MVP scope focused and avoid scope drift
Metric | Formula | Current Value | Notes
Total MVP Tasks | COUNT MVP rows | 117 | From MVP Task Tracker
Completed Tasks | Status = Done | 84 | Auto calculated
In Progress | Status = In Progress | 5 | Auto calculated
Blocked | Status = Blocked | 0 | Auto calculated
Overall Completion | Completed / Total | 71.79% | Auto calculated

## Monday-Friday Plan
InScape Giveaway MVP Monday to Friday Plan
Week | Date | Day | Main Focus | Task List | Expected Output | Status | Notes
Week 1 | 2026-05-04 | Monday | MVP scope lock and tracker alignment | • Review current tracker • Separate MVP and post-MVP tasks • Confirm essential launch items • Define MVP done criteria | MVP scope and tracker structure locked | Not Started
Week 1 | 2026-05-05 | Tuesday | Giveaway architecture and user flow | • Finalize MVP user journey • Map promo campaign creation flow • Map membership/package connection • Map entry allocation flow • Map dashboard data flow | Core user/admin flow mapped | Not Started
Week 1 | 2026-05-06 | Wednesday | Backend structure and core logic planning | • Define giveaway campaign fields • Define entry allocation data structure • Define winner selection data structure • Plan WooCommerce and Ultimate Member connection | Backend logic plan ready | Not Started
Week 1 | 2026-05-07 | Thursday | Core implementation preparation | • Start giveaway MVP code structure • Prepare reusable functions/templates • Begin campaign and membership/package connection logic • Review technical risks | Initial implementation foundation started | Not Started
Week 1 | 2026-05-08 | Friday | Review and next week preparation | • Review completed work • Update tracker • Identify blockers • Prepare next week priorities | Week 2 plan ready | Not Started
Week 2 | 2026-05-11 | Monday | Campaign creation structure | • Create/finalize campaign structure • Set campaign title/prize/details fields • Add status/start/end date logic • Prepare frontend-ready data | Admin can manage giveaway campaign data | Not Started
Week 2 | 2026-05-12 | Tuesday | WooCommerce package review | • Review package products • Define package-to-entry mapping • Plan purchase hook • Check Ultimate Member status connection | Membership/package connection plan ready | Not Started
Week 2 | 2026-05-13 | Wednesday | Entry entitlement storage | • Create user entry balance logic • Store assigned entries • Prepare used/available entry structure • Keep logic scalable | Entry entitlement foundation ready | Not Started
Week 2 | 2026-05-14 | Thursday | Campaign frontend display | • Display campaign details • Display prize info • Display campaign status • Prepare active/closed logic | Campaign display structure ready | Not Started
Week 2 | 2026-05-15 | Friday | Week 2 QA and tracker update | • Test campaign admin flow • Review package mapping • Update tracker • Prepare Week 3 coding priorities | Campaign/package foundation verified | Not Started
Week 3 | 2026-05-18 | Monday | Homepage refinement | • Refine homepage sections for MVP direction • Align homepage with giveaway revenue engine • Review CTA placement • Improve clarity for users before launch | Homepage refined for MVP messaging | Not Started
Week 3 | 2026-05-19 | Tuesday | Giveaways page refinement | • Refine giveaways listing page • Improve campaign card layout • Clarify active giveaway status • Improve entry CTA and trust flow | Giveaways page refined and MVP ready | Not Started
Week 3 | 2026-05-20 | Wednesday | Entry allocation core logic | • Build entry allocation action • Prevent over-allocation • Track campaign-wise user entries • Add success/error messages | User can allocate entries correctly | Not Started
Week 3 | 2026-05-21 | Thursday | Single giveaway page logic | • Connect entry action to single giveaway page • Show available entries • Handle logged-in/logged-out state • Show participation status | Single giveaway page becomes functional | Not Started
Week 3 | 2026-05-22 | Friday | Week 3 testing and review | • Test homepage refinement • Test giveaways refinement • Test entry allocation • Update tracker • Prepare Week 4 dashboard work | Week 3 improvements verified | Not Started
Week 4 | 2026-05-25 | Monday | User dashboard entry summary | • Show available entries • Show used entries • Show joined campaigns • Show membership/package status | Dashboard shows user giveaway summary | Not Started
Week 4 | 2026-05-26 | Tuesday | Dashboard campaign dynamics | • Show active giveaways • Show joined giveaways • Show campaign status • Show participation history | Dashboard campaign data dynamic | Not Started
Week 4 | 2026-05-27 | Wednesday | Dashboard winner status | • Prepare winner status display • Show user won/not won status • Connect with campaign winner data | Winner status area ready | Not Started
Week 4 | 2026-05-28 | Thursday | Dashboard UI integration | • Keep UI aligned with existing design • Avoid full redesign • Make data readable and usable | Dashboard MVP UI integrated | Not Started
Week 4 | 2026-05-29 | Friday | Week 4 testing and review | • Test dashboard data accuracy • Test logged-in views • Update tracker • Prepare Week 5 winner/email work | Dashboard MVP verified | Not Started
Week 5 | 2026-06-01 | Monday | Simple winner selection logic | • Build random winner selection • Validate campaign entries • Prevent no-entry winner selection • Store winner against campaign | Admin can select winner | Not Started
Week 5 | 2026-06-02 | Tuesday | Winner display logic | • Display winner on campaign/dashboard • Show winner status to user • Prepare admin winner review | Winner visible where needed | Not Started
Week 5 | 2026-06-03 | Wednesday | Entry confirmation email | • Send email after entry allocation • Keep template simple • Test wp_mail delivery | Entry confirmation email working | Not Started
Week 5 | 2026-06-04 | Thursday | Winner notification email | • Send winner notification • Keep template simple • Test email trigger | Winner email working | Not Started
Week 5 | 2026-06-05 | Friday | Basic tracking plan | • Track registration • Track package purchase • Track entry allocation • Track dashboard visits/CTA clicks | Basic MVP tracking plan ready | Not Started
Week 6 | 2026-06-08 | Monday | Full user journey testing | • Test registration/login • Test package purchase • Test entry assignment • Test entry allocation | Core user journey tested | Not Started
Week 6 | 2026-06-09 | Tuesday | Dashboard and winner testing | • Test dashboard updates • Test winner selection • Test winner display • Test email notifications | Dashboard/winner/email verified | Not Started
Week 6 | 2026-06-10 | Wednesday | Mobile and checkout testing | • Test mobile views • Test checkout behavior • Test logged-in/logged-out states | Critical frontend flows verified | Not Started
Week 6 | 2026-06-11 | Thursday | Critical bug fixing | • Fix flow-breaking bugs • Stabilize MVP logic • Review technical risks • Update documentation notes | MVP stabilized | Not Started
Week 6 | 2026-06-12 | Friday | Deployment and handover prep | • Final review • Prepare deployment • Document admin flow • Document user flow • List post-MVP items | MVP ready for launch/test | Not Started

## MVP Task Tracker
ID | Week | Date | Day | Phase | Task | Category | Priority | Status | Owner | Notes
MVP-001 | Week 1 | 2026-05-04 | Monday | MVP scope lock and tracker alignment | Review current tracker | MVP | Medium | Done | Faysal
MVP-002 | Week 1 | 2026-05-04 | Monday | MVP scope lock and tracker alignment | Separate MVP and post-MVP tasks | MVP | Medium | Done | Faysal
MVP-003 | Week 1 | 2026-05-04 | Monday | MVP scope lock and tracker alignment | Confirm essential launch items | MVP | Medium | Done | Faysal
MVP-004 | Week 1 | 2026-05-04 | Monday | MVP scope lock and tracker alignment | Define MVP done criteria | MVP | Medium | Done | Faysal
MVP-005 | Week 1 | 2026-05-05 | Tuesday | Giveaway architecture and user flow | Finalize MVP user journey | MVP | Medium | Done | Faysal
MVP-006 | Week 1 | 2026-05-05 | Tuesday | Giveaway architecture and user flow | Map promo campaign creation flow | MVP | Medium | Done | Faysal
MVP-007 | Week 1 | 2026-05-05 | Tuesday | Giveaway architecture and user flow | Map membership/package connection | MVP | Medium | Done | Faysal
MVP-008 | Week 1 | 2026-05-05 | Tuesday | Giveaway architecture and user flow | Map entry allocation flow | MVP | High | Done | Faysal
MVP-009 | Week 1 | 2026-05-05 | Tuesday | Giveaway architecture and user flow | Map dashboard data flow | MVP | Medium | Done | Faysal
MVP-010 | Week 1 | 2026-05-06 | Wednesday | Backend structure and core logic planning | Define giveaway campaign fields | MVP | Medium | Done | Faysal
MVP-011 | Week 1 | 2026-05-06 | Wednesday | Backend structure and core logic planning | Define entry allocation data structure | MVP | High | Done | Faysal
MVP-012 | Week 1 | 2026-05-06 | Wednesday | Backend structure and core logic planning | Define winner selection data structure | MVP | High | Done | Faysal
MVP-013 | Week 1 | 2026-05-06 | Wednesday | Backend structure and core logic planning | Plan WooCommerce and Ultimate Member connection | MVP | Medium | Done | Faysal
MVP-014 | Week 1 | 2026-05-07 | Thursday | Core implementation preparation | Start giveaway MVP code structure | MVP | Medium | Done | Faysal
MVP-015 | Week 1 | 2026-05-07 | Thursday | Core implementation preparation | Prepare reusable functions/templates | MVP | Medium | Done | Faysal
MVP-016 | Week 1 | 2026-05-07 | Thursday | Core implementation preparation | Begin campaign and membership/package connection logic | MVP | High | Done | Faysal
MVP-017 | Week 1 | 2026-05-07 | Thursday | Core implementation preparation | Review technical risks | MVP | Medium | Done | Faysal
MVP-018 | Week 1 | 2026-05-08 | Friday | Review and next week preparation | Review completed work | MVP | Medium | Done | Faysal
MVP-019 | Week 1 | 2026-05-08 | Friday | Review and next week preparation | Update tracker | MVP | Medium | Done | Faysal
MVP-020 | Week 1 | 2026-05-08 | Friday | Review and next week preparation | Identify blockers | MVP | Medium | Done | Faysal
MVP-021 | Week 1 | 2026-05-08 | Friday | Review and next week preparation | Prepare next week priorities | MVP | Medium | Done | Faysal
MVP-022 | Week 2 | 2026-05-11 | Monday | Campaign creation structure | Create/finalize campaign structure | MVP | Medium | Done | Faysal
MVP-023 | Week 2 | 2026-05-11 | Monday | Campaign creation structure | Set campaign title/prize/details fields | MVP | Medium | Done | Faysal
MVP-024 | Week 2 | 2026-05-11 | Monday | Campaign creation structure | Add status/start/end date logic | MVP | High | Done | Faysal
MVP-025 | Week 2 | 2026-05-11 | Monday | Campaign creation structure | Prepare frontend-ready data | MVP | Medium | Done | Faysal
MVP-026 | Week 2 | 2026-05-12 | Tuesday | WooCommerce package review | Review package products | MVP | Medium | Done | Faysal
MVP-027 | Week 2 | 2026-05-12 | Tuesday | WooCommerce package review | Define package-to-entry mapping | MVP | High | Done | Faysal
MVP-028 | Week 2 | 2026-05-12 | Tuesday | WooCommerce package review | Plan purchase hook | MVP | Medium | Done | Faysal
MVP-029 | Week 2 | 2026-05-12 | Tuesday | WooCommerce package review | Check Ultimate Member status connection | MVP | Medium | Done | Faysal
MVP-030 | Week 2 | 2026-05-13 | Wednesday | Entry entitlement storage | Create user entry balance logic | MVP | High | Done | Faysal
MVP-031 | Week 2 | 2026-05-13 | Wednesday | Entry entitlement storage | Store assigned entries | MVP | Medium | Done | Faysal
MVP-032 | Week 2 | 2026-05-13 | Wednesday | Entry entitlement storage | Prepare used/available entry structure | MVP | High | Done | Faysal
MVP-033 | Week 2 | 2026-05-13 | Wednesday | Entry entitlement storage | Keep logic scalable | MVP | High | Done | Faysal
MVP-034 | Week 2 | 2026-05-14 | Thursday | Campaign frontend display | Display campaign details | MVP | Medium | Done | Faysal
MVP-035 | Week 2 | 2026-05-14 | Thursday | Campaign frontend display | Display prize info | MVP | Medium | Done | Faysal
MVP-036 | Week 2 | 2026-05-14 | Thursday | Campaign frontend display | Display campaign status | MVP | Medium | Done | Faysal
MVP-037 | Week 2 | 2026-05-14 | Thursday | Campaign frontend display | Prepare active/closed logic | MVP | High | Done | Faysal
MVP-038 | Week 2 | 2026-05-15 | Friday | Week 2 QA and tracker update | Test campaign admin flow | MVP | Medium | Done | Faysal
MVP-039 | Week 2 | 2026-05-15 | Friday | Week 2 QA and tracker update | Review package mapping | MVP | Medium | Done | Faysal
MVP-040 | Week 2 | 2026-05-15 | Friday | Week 2 QA and tracker update | Update tracker | MVP | Medium | Done | Faysal
MVP-041 | Week 2 | 2026-05-15 | Friday | Week 2 QA and tracker update | Prepare Week 3 coding priorities | MVP | Medium | Done | Faysal
MVP-042 | Week 3 | 2026-05-18 | Monday | Homepage refinement | Refine homepage sections for MVP direction | MVP | High | Done | Faysal
MVP-043 | Week 3 | 2026-05-18 | Monday | Homepage refinement | Align homepage with giveaway revenue engine | MVP | High | Done | Faysal
MVP-044 | Week 3 | 2026-05-18 | Monday | Homepage refinement | Review CTA placement | MVP | High | Done | Faysal
MVP-045 | Week 3 | 2026-05-18 | Monday | Homepage refinement | Improve clarity for users before launch | MVP | High | Done | Faysal
MVP-046 | Week 3 | 2026-05-19 | Tuesday | Giveaways page refinement | Refine giveaways listing page | MVP | High | Done | Faysal
MVP-047 | Week 3 | 2026-05-19 | Tuesday | Giveaways page refinement | Improve campaign card layout | MVP | High | Done | Faysal
MVP-048 | Week 3 | 2026-05-19 | Tuesday | Giveaways page refinement | Clarify active giveaway status | MVP | High | Done | Faysal
MVP-049 | Week 3 | 2026-05-19 | Tuesday | Giveaways page refinement | Improve entry CTA and trust flow | MVP | High | Done | Faysal
MVP-050 | Week 3 | 2026-05-20 | Wednesday | Entry allocation core logic | Build entry allocation action | MVP | High | Done | Faysal
MVP-051 | Week 3 | 2026-05-20 | Wednesday | Entry allocation core logic | Prevent over-allocation | MVP | Medium | Done | Faysal
MVP-052 | Week 3 | 2026-05-20 | Wednesday | Entry allocation core logic | Track campaign-wise user entries | MVP | Medium | Done | Faysal
MVP-053 | Week 3 | 2026-05-20 | Wednesday | Entry allocation core logic | Add success/error messages | MVP | Medium | Done | Faysal
MVP-054 | Week 3 | 2026-05-21 | Thursday | Single giveaway page logic | Connect entry action to single giveaway page | MVP | High | Done | Faysal
MVP-055 | Week 3 | 2026-05-21 | Thursday | Single giveaway page logic | Show available entries | MVP | Medium | Done | Faysal
MVP-056 | Week 3 | 2026-05-21 | Thursday | Single giveaway page logic | Handle logged-in/logged-out state | MVP | Medium | Done | Faysal
MVP-057 | Week 3 | 2026-05-21 | Thursday | Single giveaway page logic | Show participation status | MVP | Medium | Done | Faysal
MVP-058 | Week 3 | 2026-05-22 | Friday | Week 3 testing and review | Test homepage refinement | MVP | Medium | Done | Faysal
MVP-059 | Week 3 | 2026-05-22 | Friday | Week 3 testing and review | Test giveaways refinement | MVP | Medium | Done | Faysal
MVP-060 | Week 3 | 2026-05-22 | Friday | Week 3 testing and review | Test entry allocation | MVP | High | Done | Faysal
MVP-061 | Week 3 | 2026-05-22 | Friday | Week 3 testing and review | Update tracker | MVP | Medium | Done | Faysal
MVP-062 | Week 3 | 2026-05-22 | Friday | Week 3 testing and review | Prepare Week 4 dashboard work | MVP | Medium | Done | Faysal
MVP-063 | Week 4 | 2026-05-25 | Monday | User dashboard entry summary | Show available entries | MVP | Medium | Done | Faysal
MVP-064 | Week 4 | 2026-05-25 | Monday | User dashboard entry summary | Show used entries | MVP | Medium | Review | Faysal
MVP-065 | Week 4 | 2026-05-25 | Monday | User dashboard entry summary | Show joined campaigns | MVP | Medium | Review | Faysal
MVP-066 | Week 4 | 2026-05-25 | Monday | User dashboard entry summary | Show membership/package status | MVP | Medium | Review | Faysal
MVP-067 | Week 4 | 2026-05-26 | Tuesday | Dashboard campaign dynamics | Show active giveaways | MVP | Medium | Review | Faysal
MVP-068 | Week 4 | 2026-05-26 | Tuesday | Dashboard campaign dynamics | Show joined giveaways | MVP | Medium | Review | Faysal
MVP-069 | Week 4 | 2026-05-26 | Tuesday | Dashboard campaign dynamics | Show campaign status | MVP | Medium | Review | Faysal
MVP-070 | Week 4 | 2026-05-26 | Tuesday | Dashboard campaign dynamics | Show participation history | MVP | Medium | Review | Faysal
MVP-071 | Week 4 | 2026-05-27 | Wednesday | Dashboard winner status | Prepare winner status display | MVP | High | Review | Faysal
MVP-072 | Week 4 | 2026-05-27 | Wednesday | Dashboard winner status | Show user won/not won status | MVP | Medium | Review | Faysal
MVP-073 | Week 4 | 2026-05-27 | Wednesday | Dashboard winner status | Connect with campaign winner data | MVP | High | Review | Faysal
MVP-074 | Week 4 | 2026-05-28 | Thursday | Dashboard UI integration | Keep UI aligned with existing design | MVP | Medium | Review | Faysal
MVP-075 | Week 4 | 2026-05-28 | Thursday | Dashboard UI integration | Avoid full redesign | MVP | Medium | Review | Faysal
MVP-076 | Week 4 | 2026-05-28 | Thursday | Dashboard UI integration | Make data readable and usable | MVP | Medium | Review | Faysal
MVP-077 | Week 4 | 2026-05-29 | Friday | Week 4 testing and review | Test dashboard data accuracy | MVP | Medium | Review | Faysal
MVP-078 | Week 4 | 2026-05-29 | Friday | Week 4 testing and review | Test logged-in views | MVP | Medium | Review | Faysal
MVP-079 | Week 4 | 2026-05-29 | Friday | Week 4 testing and review | Update tracker | MVP | Medium | Done | Faysal
MVP-080 | Week 4 | 2026-05-29 | Friday | Week 4 testing and review | Prepare Week 5 winner/email work | MVP | High | Post-MVP | Faysal
MVP-081 | Week 5 | 2026-06-01 | Monday | Simple winner selection logic | Build random winner selection | MVP | High | Post-MVP | Faysal
MVP-082 | Week 5 | 2026-06-01 | Monday | Simple winner selection logic | Validate campaign entries | MVP | Medium | Done | Faysal
MVP-083 | Week 5 | 2026-06-01 | Monday | Simple winner selection logic | Prevent no-entry winner selection | MVP | High | Done | Faysal
MVP-084 | Week 5 | 2026-06-01 | Monday | Simple winner selection logic | Store winner against campaign | MVP | High | Done | Faysal
MVP-085 | Week 5 | 2026-06-02 | Tuesday | Winner display logic | Display winner on campaign/dashboard | MVP | High | Done | Faysal
MVP-086 | Week 5 | 2026-06-02 | Tuesday | Winner display logic | Show winner status to user | MVP | High | Done | Faysal
MVP-087 | Week 5 | 2026-06-02 | Tuesday | Winner display logic | Prepare admin winner review | MVP | High | Done | Faysal
MVP-088 | Week 5 | 2026-06-03 | Wednesday | Entry confirmation email | Send email after entry allocation | MVP | High | Post-MVP | Faysal
MVP-089 | Week 5 | 2026-06-03 | Wednesday | Entry confirmation email | Keep template simple | MVP | Medium | Done | Faysal
MVP-090 | Week 5 | 2026-06-03 | Wednesday | Entry confirmation email | Test wp_mail delivery | MVP | Medium | Post-MVP | Faysal
MVP-091 | Week 5 | 2026-06-04 | Thursday | Winner notification email | Send winner notification | MVP | High | Post-MVP | Faysal
MVP-092 | Week 5 | 2026-06-04 | Thursday | Winner notification email | Keep template simple | MVP | Medium | Post-MVP | Faysal
MVP-093 | Week 5 | 2026-06-04 | Thursday | Winner notification email | Test email trigger | MVP | Medium | Post-MVP | Faysal
MVP-094 | Week 5 | 2026-06-05 | Friday | Basic tracking plan | Track registration | MVP | Medium | Done | Faysal
MVP-095 | Week 5 | 2026-06-05 | Friday | Basic tracking plan | Track package purchase | MVP | Medium | Done | Faysal
MVP-096 | Week 5 | 2026-06-05 | Friday | Basic tracking plan | Track entry allocation | MVP | High | Done | Faysal
MVP-097 | Week 5 | 2026-06-05 | Friday | Basic tracking plan | Track dashboard visits/CTA clicks | MVP | Medium | Done | Faysal
MVP-098 | Week 6 | 2026-06-08 | Monday | Full user journey testing | Test registration/login | MVP | Medium | Done | Faysal
MVP-099 | Week 6 | 2026-06-08 | Monday | Full user journey testing | Test package purchase | MVP | Medium | Done | Faysal
MVP-100 | Week 6 | 2026-06-08 | Monday | Full user journey testing | Test entry assignment | MVP | High | Done | Faysal
MVP-101 | Week 6 | 2026-06-08 | Monday | Full user journey testing | Test entry allocation | MVP | High | Done | Faysal
MVP-102 | Week 6 | 2026-06-09 | Tuesday | Dashboard and winner testing | Test dashboard updates | MVP | Medium | Done | Faysal
MVP-103 | Week 6 | 2026-06-09 | Tuesday | Dashboard and winner testing | Test winner selection | MVP | High | Review | Faysal
MVP-104 | Week 6 | 2026-06-09 | Tuesday | Dashboard and winner testing | Test winner display | MVP | High | Done | Faysal
MVP-105 | Week 6 | 2026-06-09 | Tuesday | Dashboard and winner testing | Test email notifications | MVP | Medium | Post-MVP | Faysal
MVP-106 | Week 6 | 2026-06-10 | Wednesday | Mobile and checkout testing | Test mobile views | MVP | Medium | Done | Faysal
MVP-107 | Week 6 | 2026-06-10 | Wednesday | Mobile and checkout testing | Test checkout behavior | MVP | Medium | Done | Faysal
MVP-108 | Week 6 | 2026-06-10 | Wednesday | Mobile and checkout testing | Test logged-in/logged-out states | MVP | Medium | Done | Faysal
MVP-109 | Week 6 | 2026-06-11 | Thursday | Critical bug fixing | Fix flow-breaking bugs | MVP | Medium | In Progress | Faysal
MVP-110 | Week 6 | 2026-06-11 | Thursday | Critical bug fixing | Stabilize MVP logic | MVP | High | In Progress | Faysal
MVP-111 | Week 6 | 2026-06-11 | Thursday | Critical bug fixing | Review technical risks | MVP | Medium | In Progress | Faysal
MVP-112 | Week 6 | 2026-06-11 | Thursday | Critical bug fixing | Update documentation notes | MVP | Medium | In Progress | Faysal
MVP-113 | Week 6 | 2026-06-12 | Friday | Deployment and handover prep | Final review | MVP | Medium | Review | Faysal
MVP-114 | Week 6 | 2026-06-12 | Friday | Deployment and handover prep | Prepare deployment | MVP | Medium | Review | Faysal
MVP-115 | Week 6 | 2026-06-12 | Friday | Deployment and handover prep | Document admin flow | MVP | Medium | Review | Faysal
MVP-116 | Week 6 | 2026-06-12 | Friday | Deployment and handover prep | Document user flow | MVP | Medium | Review | Faysal
MVP-117 | Week 6 | 2026-06-12 | Friday | Deployment and handover prep | List post-MVP items | MVP | Medium | In Progress | Faysal

## Post-MVP
Post-MVP Item | Reason to Keep Post-MVP | Priority | Status | Notes
Advanced SEO | Important after live MVP and content validation | High | Post-MVP | Google SEO, schema, metadata, indexing
Full code optimization | Deeper optimization after MVP behavior is validated | High | Post-MVP | Refactor, asset loading, Core Web Vitals
Advanced email automation | Only after basic MVP emails and user flows are validated | Medium | Post-MVP | Segmentation, renewal, abandoned checkout
Advanced analytics dashboard | Requires enough user data after launch | Medium | Post-MVP | Performance dashboard and reporting
Winner history and transparency | Useful for trust after first campaigns | Medium | Post-MVP | Public winner archive
Referral/viral sharing system | Growth feature after core giveaway works | Medium | Post-MVP | Referral tracking and rewards
Advanced fraud prevention | Can be enhanced after real user behavior appears | High | Post-MVP | Anti-abuse controls
Multi-country giveaway logic | Expansion feature after first market validation | Low | Post-MVP | Country eligibility and compliance
Advanced reporting | Can be built after stable campaign model | Medium | Post-MVP | Campaign performance reports
Deep dashboard polish | UI enhancement after functionality is validated | Low | Post-MVP | Animations and refined UX

## Options
Status | Priority | Phase | Owner
Not Started | High | MVP | Faysal
In Progress | Medium | Post-MVP | Jim
Blocked | Low | Support | Faysal + Jim
Review | Critical |  | TBD
Done
Post-MVP